STEP 1: Document Inspection

- Request for Inspection (RFI):

- - This is submitted by Material Controller to QA/QC 24 hours before inspection.

- Purchase Order (PO)

- - Confirms items ordered, material specification/grade, quantity, etc.

- - QC Role:

- ·  The description on the PO vs the actual material delivered

- ·  The size and specification on the PO vs the item’s marking

- PO contains a unique PO Number, Supplier and Buyer info, Item details (description, quantity, unit of measure etc), prices (unit and total), delivery date & location, and terms & conditions including payment and delivery terms.

- Approved Vendor List (AVL):

- - Its a list of approved vendors by Aramco.

- - QC Role:
·  QC must verify that the manufacturer listed on the MTC is actually an Aramco Approved.

- The Approved Vendor List (AVL) is a control list of suppliers/manufacturers that Saudi Aramco has qualified and accepted to supply specific materials or equipment.

- Delivery Note

- - Ensures the delivery material are correctly described regarding quantity and items.

- - QC Role:

- ·  QC ensure Item Description / Material Type against PO

- ·  Ensure PO Number is correct in Delivery note and quantity received

- A delivery note is a supplier-issued document that lists what is being delivered.

- Mill Test Certificates

- - It contains Heat no, Material Specifications, Mechanical Properties and Chemical Properties

- - QC Role:

- ·  QC ensure Heat/batch number traceability

- ·  Ensure mechanical tests (e.g., tensile, impact where applicable)

- MTC is a quality document issued by the manufacturer that proves the material supplied meets the required standards

- Inspection Release Note (IRN) or Inspection Release Certificate (IRC)

- - IRN shows the supplier’s items were inspected and approved for shipment before reaching site

- - IRC is a formal certificate confirming that inspected items passed the inspection criteria.

- - QC Role:

- ·  QC ensure PO number is correct

- ·  Confirm pre-shipment inspection was completed

- IRN conatin things like PO Number, Order Details,IRN Number and date etc

- IRC contains things like PO Number,released item description and client info etc

- SATIP / SAIC:

- We have also SATIP and respective SAIC like if the activity is shop fabrication the satip will be SATIP-L-350-08 and the saic used for pipe visual inspection and document review is SAIC-L-2005
- QC Role:

- ·  Proceed the work as per SATIP

- ·  Check the things in SAIC

- 8) PMI Report (For Alloy Materials only)

- - Positive Material Identification is required for all stainless steel and alloy piping (Chromium/Moly).

- - QC Role:

- ·  Confirm a PMI Report is attached for any material other than standard Carbon Steel.

- ·  Verify the PMI machine’s calibration certificate is included in the document package.

- QC role in Step 1:

- Match PO to Delivery Note.

- Validate Vendor Approval.

- MTC & Traceability.

- SATIP & SAIC

- STEP 2: VISUAL INSPECTION

- Material Visual Inspection

- -  Inspecting the physical condition of the pipe/fittings for damage during transit.

- -  QC Role:

- ·  Check for mechanical damage (dents, pits, deep scratches, or gouges).

- ·  Verify end protectors (plastic caps/wood) are in place to prevent debris entry.

- Dimensional Verification

- -  Ensure the material matches the required specs.

- -  QC Role:

- ·  Verify the Schedule (e.g., Sch 40, 80, XS) using a calibrated Thickness Gauge or Vernier Caliper.

- ·  Diameter: Check the Outside Diameter (OD) against ASME B36.10 (for CS) or B36.19 (for SS).

- QC role in Step 2:

- Check for mechanical damage and ensure end protection

- Verify Wall Thickness (Schedule) and OD

- STEP 3: VISUAL INSPECTION

- Material Receiving Inspection Report (MRIR)

- -  This is the formal report used to record and confirm all inspection results.

- -  QC Role:

- ·  Prepare the MRIR with complete details like item name, quantity, heat number, PO, and inspection outcomes.

- ·  Complete the SAIC checklist showing documents reviewed, visual/physical checks done, and acceptance status.

- Non-Conformance Reporting (NCR)

- -  For any item that fails inspection or does not comply with requirements.

- -  QC Role:

- ·  Raise a NCR listing exact defects or issues (e.g., damage, wrong marking, missing test report).

- ·  Tag and place the non-conforming items in the “Hold” or quarantine area per procedure.

- PIPING QC Role in MR:

- Match PO to Delivery Note.

- Validate Vendor Approval.

- MTC & Traceability.

- Check for mechanical damage and ensure end protection

- Verify Wall Thickness Schedule and OD

- Prepare MRIR (inspection report)

- Raise NCR for non-conforming items

- Scenario - Missing or Incorrect Mill Test Certificate (MTC)

- When: During material receiving inspection, a batch of piping (e.g., carbon steel pipes) arrives but no Mill Test Certificate or incomplete/incorrect MTC is provided.

- Flow of NCR:

- Detect & Identify: I found missing MTC during document review and marks material as non‑conforming.

- Hold & Segregate: I marked material with a HOLD Tag and moved to quarantine.

- Raise NCR: I raises an NCR with details:NCR number, Heat Numbers, Supplier info, PO number & location etc

- Description: Missing MTC or incomplete certificate

- Immediate Containment: I instructs Material Control to not release material for use

- Notification:  I take the sign of supervisor and share iNCR with supplier and PID.

- Corrective Action: Supplier must provide correct MTC or reissue complete MTC.

- Re‑Inspection: QC re‑checks material after receiving correct MTC.

- Closure: Once MTC is verified and accepted, QC closes the NCR with sign‑off.